## mini-project_schedule
Android Based Home Automation System with Speech Recognition using Arduino and Python
| Tasks | [5 empty] | Presentation Format and Procedure
[6 empty] | Sl.no | Steps | Priority
Sl. No | Task | Due | Status | Assigned to |  | 1 | Title of the Project | Yes
1 | Python mobile App(Android/IOS) | - | Done | Tejas |  | 2 | Introduction | Yes
2 | Bluetooth Connectivity between Android Application and hardware | - | Done | Tejas |  | 3 | Speech | Yes
3 | Component Selection | before 2nd internals |  | Indukanth |  | 4 | Speech Recognition | Yes
4 | Simulation with Proteus | before 2nd internals |  | Sai Ritwik |  | 5 | Arduino | -
5 | Source Code for Arduino | before 3rd internals |  | Sai Ritwik |  | 6 | Hardware Structure | -
6 | Testing android app with hardware | before 3rd internals |  | Sai Ritwik/Tejas |  | 7 | Hardware Connection (With screenshot of circuit connection from Proteus) | -
7 | Presentation on the project | before 3rd internals |  | Kiran |  | 8 | Arduino Source Code Screenshot | -
8 | Report for project | before 3rd internals |  | Kiran/Indukanth |  | 9 | Speech Recognition in Android application | -
[6 empty] | 10 | Android application using Python | -
[6 empty] | 11 | Screenshot of mobile App (With bluetooth Paired Devices) | -
[6 empty] | 12 | Improvements | -
[6 empty] | 13 | Conclusion | -
| Courses |  |  |  |  | 14 | References | -
Sl.no | Course | Assigned to |  |  |  | 15 | Last Page (Thank You) | Yes
1 | Basics of Arduino | All
2 | Basics of Python | All
3 | C++ Basics | All |  |  | References
4 | TinkerCad | Tejas and Sai |  | Sl.no | References
5 | Proteus | Tejas and Sai |  | 1
6 | Basic Electronics | All |  | 2
7 | Concepts of Microcontroller | All |  | 3
4
5
6
7